## SCCM PLAN
Sr.No. | Phase | TASK Details | Start Date | End Date | Responsibility | Status | Comment
1 | SCCM project initialization | SCCM PRODUCTION SETUP (Initialization, POC, Server procurement & setup)
2 | SCCM project initialization | Initialization
3 | SCCM project initialization | Kick off meeting for planning and execution with SCCM team
4 | SCCM Requirement gathering&Analysis | Requirement gathering and review of Environment
5 | SCCM Requirement gathering&Analysis | Planning & Review
6 | SCCM Requirement gathering&Analysis | AD Infrastruture Documenation and diagram
7 | SCCM Requirement gathering&Analysis | Network information and diagram
8 | SCCM Requirement gathering&Analysis | Network Bandwidth Information
9 | SCCM Requirement gathering&Analysis | Network Bandwidth utilization Information
10 | SCCM Requirement gathering&Analysis | Branch Servers information
11 | SCCM Requirement gathering&Analysis | POC network Diagram for POC setup
12 | SCCM Requirement gathering&Analysis | & branch wise user count and total users /computer estimate
13 | SCCM Requirement gathering&Analysis | Current Desktop Environment & standardization
14 | SCCM Requirement gathering&Analysis | complete infrastructure study and discussion
15 | SCCM Design | Design
16 | SCCM Design | Production Architecture Design Consideration
17 | SCCM Design | Number of servers required in for SCCM Setup
18 | SCCM Design | Operating system requirement for SCCM Servers in
19 | SCCM Design | SCCM Verison Required in
20 | SCCM Design | SQL DATABASE Version requirement for SCC
21 | SCCM Design | SCCM Servers hardware configuration requirement
22 | SCCM Design | Capabilities to be Included in SCCM Design in Phase manner
23 | SCCM Design | Service PACK Requirement
24 | SCCM Design | Determine Whether to Extend the Active Directory Schema for Configuration Manage
25 | SCCM Design | Planning for Discovery in Configuration Manage
26 | SCCM Design | Planning for Client Settings in Configuration Manager
27 | SCCM Design | How many Secondary Sites in
28 | SCCM Design | How many DP's in USA and detail designing
29 | SCCM Design | Planning for Boundaries and Boundary Groups in Configuration Manager
30 | SCCM Design | Planning for Communications in Configuration Manager.
31 | SCCM Design | Planning for Site Operations in Configuration Manager.
32 | SCCM Design | Planning for High Availability with Configuration Manager.
33 | SCCM License | SCCM license
34 | SCCM License | First level discussion with the team on license procurement
35 | SCCM License | Raise internal request with IMS
36 | SCCM License | Procure the license from Microsoft
37 | POC Setup | POC Setup implementation
38 | POC Setup | Implement SCCM phase - 1 with test FOREST A
39 | POC Setup | Implement SCCM phase - 2 with test FOREST B
40 | POC Setup | SCCM Implement and test system site roles for SCCM setup
41 | POC Setup | Software Inventory
42 | POC Setup | Hardware inventory
43 | POC Setup | Patch management
44 | POC Setup | Software deployment
45 | POC Setup | Remote management
46 | POC Setup | OS deployment
47 | POC Setup | Software metering
48 | POC Setup | Session with to share the results of the POC
53 | SCCM Installation Perquisites | Implementation Phase -
54 | SCCM Installation Perquisites | Raise Hardware Server Requirement with
55 | SCCM Installation Perquisites | Raise Operating System Server Requirement with
56 | SCCM Installation Perquisites | Raise additional storage space with
57 | SCCM Installation Perquisites | Installation of Windows Enterprise Edition -64 bit for Stand alone Primary Site.
58 | SCCM Installation Perquisites | Installation of SQL with latest Service Pack on Stand alone Primary Site server only.
59 | SCCM Installation Perquisites | Installation of Windows Enterprise Edition -64 bit for other Site roles
60 | SCCM Installation Perquisites | Installation of Windows Enterprise Edition -64 bit for cold backup server
61 | SCCM Installation Perquisites | Check SCCM Servers infrastructure readyness with
62 | SCCM Installation Perquisites | Create AD Groups and Service accounts for SCCM and SCCM SQL Database
63 | SCCM Installation Perquisites | Delegate appropriated rights to SCCM admin User
64 | SCCM Installation Perquisites | System Container creation and permission assignmen
65 | SCCM Installation Perquisites | Provide Computer Account of SCCM Primary and Secondary site Server Full Rights to System Container
66 | SCCM Installation Perquisites | Site Server Prerequisites such as .net framework 4 , BITS ,Windows updates,WDS,WAI
67 | SCCM Installation Perquisites | add site server computer name and sccm admin user to local administrator group on primary stand alone site server.
68 | SCCM Installation Perquisites | AD Schema Extension SMSSetup\Bin\x64\Extadsch.exe, right click and choose Run As Administrator
69 | SCCM Installation Perquisites | Check log file and see if AD schema extended successfully. Verify the same
70 | INSTALLATION | SCCM Primary standalone site installation
71 | INSTALLATION | Download SCCM 2012 SP1 from Microsoft Site and put on Primary Site Server
72 | INSTALLATION | Start execution of SCCM 2012 SP1 on Server and select " Install Confuguration Primary Site"
73 | INSTALLATION | Put the License Product Ke
74 | INSTALLATION | Accept the License Teams and Condition
75 | INSTALLATION | Check for Pre-requisite requiremen
76 | INSTALLATION | Select Client Language Selection - English
77 | INSTALLATION | Site and installation Settings - Put the Unique Site Name and put Installation pat
78 | INSTALLATION | Select Configuration Manager Console option on Site and installation Settings.
79 | INSTALLATION | Select Primary Stand alone site option
80 | INSTALLATION | Select Server Language Selection - Englis
81 | INSTALLATION | Put the Database information. - DATABASE Server name
82 | INSTALLATION | Put the SMS Provider Siettings
83 | INSTALLATION | Client Communication Setting. -HTTS
84 | INSTALLATION | Install Management Point [MP]on this Primary Site server and point to Site Role Server
85 | INSTALLATION | nstall Distrubution Point [DP] on this Primary Site server and point to Site Role Server
86 | INSTALLATION | Prerequisite Check and installation.
87 | INSTALLATION | Installation of SCCM 2012 and over all Progress
88 | INSTALLATION | SCCM 2012 SP1 Installation Complete
89 | INSTALLATION | Verify the logs and installation errors if any
90 |  | SCCM primary site configuration
91 |  | Configure Active Directory Forest Discovery
92 |  | Configure Active Directory Group Discover
93 |  | Configure Active Directory System Discover
94 |  | Configure Active Directory User Discovery
95 |  | Configure and create Boundaries and Boundary Groups for Site.
96 |  | Configure Client Push Installation for SCCM Client installation on all Desktops
97 | SCCM Plan | Check for error logs and make all desktops have SCCM clien
98 |  | Add the WSUS Update Services 3.0 SP2 rol
99 |  | WSUS role installed as part of the Software Update Point role installation
100 |  | install the SUP Role on our Standalone Primary Server
101 |  | Verify the Patches syncronized from Microsoft.
102 |  | Install Distrubution Point on Site Role Seve
103 |  | Configure Distrubution Point [DP] Point
104 |  | Check for error logs
105 |  | Verify the Distrubution Point Site Role Installation
106 |  | Install Application Catlog web Service Point Site Role Seve
107 |  | Configure Application Catlog web Service Poin
108 |  | Check for error logs
109 |  | Verify the Application Catlog web Service Point Site Role Installation
110 |  | Install Application Catlog web Site Point Site Role Sever
111 |  | Configure Application Catlog web Site Point
112 |  | Check for error logs
113 |  | Verify the Application Catlog web Site Site Role Installation
114 |  | Install Management Point Site Role Sever
115 |  | Configure Management Point Site Rol
116 |  | Check for error logs
117 |  | Verify the Management Point Site Role Installation
118 |  | Install Reporting Service Point Site Role Seve
119 |  | Configure Reporting Service Point
120 |  | Check for error logs
121 |  | Verify the Reporting Service Point Site Role Installation
122 |  | Install Asset Intelligence Point Point Site Role Sever
123 |  | Configure Asset Intelligence Poin
124 |  | Check for error logs
125 |  | Verify the Asset Intelligence Point Site Role Installatio
126 |  | Configure Software Inventor
127 |  | Check for error logs
128 |  | Verify and Test the Software Inventory.
129 |  | Configure Hardware Inventor
130 |  | Check for error logs
131 |  | Verify and Test the hardware Inventory.
132 |  | Configure Remote Services in SCC
133 |  | Check for error logs
134 |  | Verify and Test the Remote Services using SCC
135 |  | Configuration of SCCM reporting
136 |  | Verify reporting
137 |  | Configuration of Backup of Primary site and SQL Database
138 |  | SCCM Phase - 1 Verification and Validation
139 |  | Check all Computer Systems reported to SCCM Primary Site
140 |  | Check for Software inventory for all computers using SCCM
141 |  | Check for Hardware inventory for all computers using SCCM
142 |  | Check Software deployment using SCCM
143 |  | Check Patches Deployement using SCCM
144 |  | Check Remote Functionality using SCCM
145 |  | Verify Backup status (SCCM site and SQL DB backup)
146 |  | SCCM 2012 implemenation Confirmation in USA Domain Enviroment
191 |  | SCCM Phase - 2 Verification and Validation
192 |  | Check all Computer Systems reported to SCCM Primary Site for enviroment
193 |  | Check for Software inventory for all computers using SCCM for enviroment
194 |  | Check for Hardware inventory for all computers using SCCM for enviroment
195 |  | Check Software deployment using SCCM for enviroment
196 |  | Check Patches Deployement using SCCM for enviroment
197 |  | Check Remote Functionality using SCCM for enviroment
198 |  | Verify Backup status (SCCM site and SQL DB backup) for enviroment
199 |  | SCCM 2012 implemenation Confirmation in Domain Enviroment